## Iteration Estimated Effort
Roles:
| UI Designers | Sarah, Joshua, Mathewos, Scott
| Communicator | Sarah
| Developers | Sarah, Joshua, Mathewos, Scott
| QA Engineer | Mathewos
| Marketing Strategist | Scott
| SEO Specialist | Scott
Task Name: (Dependencies top to bottom) | [8 empty] | Sarah | Joshua | Mathewos | Scott | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 3 |  | 2.5
|  | Gather | Communicator | Sarah | 1 |  | 0 | [5 empty] | 0
|  | Analyze | Marketing Strategist | Scott | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Specify | SEO Specialist | Scott | 1 |  | 0.5 |  |  |  |  | 0.5 | 0.5
| Client communication |  |  |  |  | 4 |  | 1
|  | Client Zoom Meeting | Communicator / Developers | Sarah | 4 |  | 1 |  |  |  |  | 1 | 1
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Design & Build
Iteration 1: | Research and design |  |  |  |  | 15 |  | 12.9
|  | Decide on design tools | Developers | All | 2 |  | 2.5 |  | 1 | 1 |  | 0.5 | 2.5
|  | Research | Developers | All | 8 |  | 4.4 |  | 2 | 0.4 |  | 2 | 4.4
|  | Create website mock-ups | UI Designers | All | 5 |  | 4.5 |  | 2 | 2 |  | 0.5 | 4.5
| Client Communication |  |  |  |  | 1.5 |  | 5.5
|  | Communicate with Amy on design ideas and get feedback | Communicator | Sarah | 1 |  | 1.5 |  | 1.5 |  |  |  | 1.5
|  | Update client on current progress | Communicator |  | 0.5 |  | 1 |  | 1 |  |  |  | 1
| Development |  |  |  |  | 12.5 |  | 6
|  | Project set up | Developers | Scott, Joshua | 3 |  | 3 |  |  |  |  | 3 | 3
|  | Home Page set up | Developers | All | 8 |  | 0 | [5 empty] | 0
|  | Test Home Page | QA Engineer | Mathewos | 1.5 |  | 1 |  |  |  | 1 |  | 1
| Iteration planning |  |  |  |  | 4 |  | 2
|  | Iteration 2 Planning | Developers | All | 4 |  | 2 |  | 1 |  |  | 1 | 2
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Iteration 2:
| Client Communication |  |  |  |  | 1 |  | 0
|  | Update client on current progress | Communicator | Sarah | 1 |  | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Development |  |  |  |  | 35 |  | 0
|  | Home Page set up | Developers | Joshua | 2 |  | 0 | [5 empty] | 0
|  | About Us Page set up | Developers | Mathewos | 2 |  | 0 | [5 empty] | 0
|  | Providers Page set up | Developers | Scott | 8 |  | 0 | [5 empty] | 0
|  | Services Page set up | Developers | Sarah | 12 |  | 0 | [5 empty] | 0
|  | Facebook Configuration Plugin | Developers | Scott | 1
|  | Wordpress configuration and seo setup | Developers | Scott | 10 |  | 0 | [5 empty] | 0
| Iteration planning |  |  |  |  | 4 |  | 0
|  | Iteration 3 Planning | Developers | All | 4 |  | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Iteration 3:
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Total |  |  |  |  | 80 |  | 22.4 |  | 8.5 | 3.4 | 1 | 9.5 | 22.4